## Slide 1
EPD Incentive Platform
Executive Summary
Kazakhstan & CIS | Digital Incentive Management System
April 2026 | CONFIDENTIAL

## Slide 2
01 | Objective
What we are building and why
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
2 / 7
Design, develop, and deploy a centralized web-based platform that automates the quarterly incentive calculation, review, and sign-off process for Abbott's EPD (Established Pharmaceuticals Division) field force across Kazakhstan and the CIS region.
🎯
Accuracy
Eliminate manual Excel errors by enforcing validated, formula-driven calculations backed by a normalized PostgreSQL database on Supabase.
⚡
Efficiency
Reduce incentive cycle time from weeks to days via automated workflows, real-time dashboards, and digital sign-off routing.
👁️
Transparency
Provide role-based visibility (DVP → RBM → FLM → Med. Rep.) so every stakeholder owns their data with audit-ready records.

## Slide 3
02 | High-Level Scope
Boundaries, inclusions & phased delivery
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
3 / 7
✅ IN SCOPE
Phase 1 – Data & Infra
Normalized Supabase schema (13 tables), CSV-to-DB seed pipelines, RLS security policies
Phase 2 – Core Dashboard
Next.js 14 role-based portal: Summary, Detailed, Sign-Off, Product Promo views
Phase 3 – Analytics
Quarter-over-quarter trend analysis, top-performer leaderboards, exportable Excel/PDF reports
Phase 4 – Auth & Roles
Supabase Auth SSO: DVP, RBM, FLM, Med. Rep. with scoped data access
Phase 5 – Automation
Automated quarterly data ingestion, e-signature sign-off workflow, email notifications
Geography
Kazakhstan (KZ) + Georgia (Country 87) with multi-currency LC/USD reporting
🚫 OUT OF SCOPE
✗ ERP / SAP integration (future phase)
✗ Mobile native app (web-responsive only)
✗ Global markets outside KZ / Georgia
✗ Payroll system direct write-back
~90
Reps per Quarter
13
DB Tables
4
Delivery Phases
5
User Roles
DELIVERY TIMELINE
P1 Done
P2 In Progress
P3 Planned
P4-5 Roadmap

## Slide 4
03 | Problem Statement
Current-state pain points driving this initiative
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
4 / 7
⚠️ Current State: Quarterly incentive calculations are managed entirely in a complex, multi-sheet Excel workbook with 9 inter-linked CSVs — creating significant risk of manual errors, version conflicts, and delayed approvals.
📊 Manual Data Entry & Calculation Errors
9 inter-linked CSV/Excel files with no data validation layer. Comma-formatted numbers (e.g., '395,525.00'), Cyrillic character mismatches, and staggered column headers cause import failures and silent data corruption each quarter.
🗃️ No Single Source of Truth
Incentive data is scattered: Staff_Input.csv, Mapping.csv, TCFA.csv, TIC.csv, Summary_calculation.csv, and others. Any change to one file is not propagated — leading to inconsistencies between manager views and rep payouts.
🔓 Zero Role-Based Access Control
A single shared Excel file is emailed to all stakeholders. DVPs can see confidential data of all regions; FLMs can inadvertently overwrite other teams' records. There is no audit trail of who changed what and when.
⏳ Slow Sign-Off & Approval Cycle
The sign-off process requires manual email chains between DVPs, RBMs, and FLMs. A single revision request can stall the cycle by 5–10 business days, delaying rep payments and reducing field-force morale.
📉 No Historical Analytics or Trends
Each quarter's data lives in a separate Excel version. Year-over-year performance comparisons, rep attrition impact, and product-level trend analysis are impossible without costly manual consolidation effort.
📦 Scalability Bottleneck
Adding a new quarter requires regenerating the entire 107KB static JS data file. Adding a country, product, or promo-line requires structural changes to all inter-linked sheets — not scalable as EPD expands.

## Slide 5
04 | Technical Architecture
System design & integration layers
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
5 / 7
PRESENTATION LAYER – Next.js 14 (App Router)
API / BFF LAYER – Next.js API Routes & Server Actions
DATA LAYER – Supabase PostgreSQL (13 Tables + RLS)
INFRASTRUCTURE LAYER
Summary
Dashboard
KPI cards
Quarter filters
Detailed
View
Rep-level
product breakdown
Product
Promo
Portfolio
achievement
Sign-Off
Workflow
Digital approval
e-signature
Staff
Management
Rep roster
leave tracking
Auth Middleware
(Role Guard)
Data Fetch
Server Actions
Export API
(Excel / PDF)
Sign-Off API
Workflow Engine
representatives
quarterly_performance
product_performance
incentive_calculations
tcfa_scores
promo_line_products
regions / cities
positions / quarters
RLS Policies
(Row-Level Security)
Supabase Cloud
(PostgreSQL + Auth)
Vercel Edge
(Next.js Hosting)
GitHub Actions
(CI/CD Pipeline)
Supabase Storage
(CSV Exports)
Environment Secrets
(.env / Vault)
▼
▼
▼

## Slide 6
05 | Risk Register
Identified risks with mitigation strategies
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
6 / 7
#
Risk Description
Likelihood
Impact
Mitigation Strategy
R01
Data quality issues from source CSVs (Cyrillic names, comma-formatted numbers, blank columns)
HIGH
HIGH
Pre-migration data cleanse script; strict TypeScript validators; dedicated QA pass comparing DB output vs. source Excel row-by-row.
R02
Supabase service outage or free-tier limitations during critical quarter close
LOW
HIGH
Export read-only Excel fallback at quarter open; Pro-tier upgrade SLA for go-live; nightly pg_dump backups to Supabase Storage.
R03
Scope creep from additional country onboarding (Georgia / Country 87) or new promo lines mid-quarter
MED
MED
Change-control board approval required; modular schema allows country/region rows without structural changes; phased rollout plan.
R04
User adoption resistance from field force / managers accustomed to Excel workflows
MED
HIGH
Hypercare support during Q1 go-live; in-app contextual tooltips; training sessions per role tier (DVP, RBM, FLM); Excel export always available.
R05
Delay in sign-off chain blocking quarterly payroll processing timelines
LOW
HIGH
Automated email reminders at 48hr & 24hr before deadline; escalation flag in DVP dashboard; offline approval workaround via PDF export.
R06
Security / unauthorized access to sensitive incentive and salary data via misconfigured RLS
LOW
HIGH
Supabase Row Level Security enforced at DB layer; penetration test prior to launch; role tokens scoped per user; audit logs enabled.

## Slide 7
06 | Dependency Register
External dependencies required for successful delivery
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
7 / 7
CAT
ID
Dependency Name
Owner
Phase
Status
Description / Notes
T
D01
Supabase Project (Prod)
BSS / IT
Phase 1
PENDING
Production Supabase project with Pro tier subscription. URL & service_role key required for DB schema deployment and seeding.
T
D02
Vercel Deployment Account
BSS / IT
Phase 2
PENDING
Vercel Pro or Abbott-managed hosting for Next.js app. Custom domain (epd-incentive.abbott.com) DNS record required.
T
D03
GitHub Repository & CI/CD
BSS
Phase 1
DONE
GitHub repo (Arslan664/EPD_Incentive_Calculator) is live. GitHub Actions workflow for lint, test, and Vercel deploy to be configured.
D
D04
Complete Q1–Q4 Source CSVs (all quarters)
Abbott KZ Team
Phase 1
PARTIAL
Q1 2017 and Q2 2017 CSVs available. Q3/Q4 and 2018+ data required for full historical load. Georgia (Country 87) records needed.
D
D05
BC_KZ_2017_V10_FINAL.XLSM (External Formulas)
Abbott KZ Team
Phase 1
PENDING
Source Excel file containing linked formula definitions referenced in Summary_calculation sheet. Required to validate seed script accuracy.
P
D06
Abbott DVP Sign-Off on Roles & Access Matrix
Abbott Management
Phase 2
PENDING
Formal approval of RBAC matrix: which role (DVP/RBM/FLM/Rep) sees which data. Required before Supabase Auth configuration begins.
P
D07
UAT Participants (FLMs & RBMs for pilot quarter)
Abbott KZ HR
Phase 3
NOT STARTED
Minimum 3 FLMs + 1 RBM to conduct structured UAT against Q2 2017 data. Feedback window: 5 business days.
P
D08
Exchange Rate Policy (LC/USD historical locking)
Abbott Finance
Phase 1
PENDING
Decision required: lock historical rates per quarter at time of ingestion (Q1=314.79, Q2=332.70) or allow finance team override.
STATUS KEY:
DONE
PARTIAL
PENDING
NOT STARTED
CRITICAL