## Slide 1
EPD Incentive Platform
Executive Summary
Kazakhstan & CIS | Digital Incentive Management System
April 2026 | CONFIDENTIAL

## Slide 2
01 | Objective
What we are building and why
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
2 / 8
Design, develop, and deploy a centralized web-based platform that automates the quarterly incentive calculation, review, and sign-off process for Abbott's EPD (Established Pharmaceuticals Division) field force across Kazakhstan and the CIS region — with a roadmap to scale to 70+ countries and 5,000–10,000 representatives globally.
🎯
Accuracy
Eliminate manual Excel errors via validated, formula-driven calculations backed by a normalized PostgreSQL database on Supabase. Reduce 2% error rate on 75M LC payouts.
⚡
Efficiency
Reduce the monthly close cycle from 2–3 weeks to under 48 hours via automated workflows, real-time dashboards, and digital multi-level sign-off routing.
👁️
Transparency
Provide role-based visibility (DVP → RBM → FLM → Med. Rep.) across Kazakhstan's 86 reps, 8 quarters, 15 products, and 6 promo lines — with full audit trail.

## Slide 3
02 | High-Level Scope
Boundaries, inclusions & phased delivery
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
3 / 8
✅ IN SCOPE
Phase 1 – Data & Infra
Normalized Supabase schema (13 tables), CSV-to-DB seed pipelines, RLS security policies
Phase 2 – Core Dashboard
Next.js 14 role-based portal: Summary, Detailed, Sign-Off, Product Promo, Staff views
Phase 3 – Analytics
Quarter-over-quarter trend analysis, top-performer leaderboards, Excel/PDF export reports
Phase 4 – Auth & Roles
Supabase Auth SSO: DVP, RBM, FLM, Med. Rep. with scoped data access and audit logs
Phase 5 – Automation
Quarterly data ingestion pipeline, e-signature sign-off workflow, email notifications
Geography
Kazakhstan (86 reps, 8 qtrs) as POC; roadmap to 70+ countries, 5,000–10,000 reps
🚫 OUT OF SCOPE
✗ ERP / SAP integration (future phase)
✗ Mobile native app (web-responsive only)
✗ Global markets outside KZ / Georgia
✗ Payroll system direct write-back
86
Reps Tracked
8
Quarters Live
15
Products
6
Promo Lines
DELIVERY TIMELINE
P1 Done
P2 In Progress
P3 Planned
P4-5 Roadmap

## Slide 4
03 | Problem Statement
Current-state pain points driving this initiative
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
4 / 8
⚠️ Current State: Quarterly incentive calculations are managed entirely in a complex, multi-sheet Excel workbook with 9 inter-linked CSVs — creating significant risk of manual errors, version conflicts, and delayed approvals for 86 representatives across Kazakhstan.
📊 Manual Calculation Errors
9 inter-linked CSV/Excel files with no validation. Comma-formatted numbers, Cyrillic character mismatches, and staggered headers cause import failures. A 2% error rate on 75M LC annual payouts = M in incorrect payments.
🗃️ No Single Source of Truth
Data scattered across Staff_Input, Mapping, TCFA, TIC, Summary_calculation, and 4 more CSVs. Changes in one file are not propagated — creating inconsistencies between manager views and rep payout records.
🔓 Zero Role-Based Access
A single shared Excel file is emailed to all stakeholders. DVPs see confidential data of all regions; FLMs can overwrite other teams' records. No audit trail of who changed what and when — a SOX compliance risk.
⏳ Slow Sign-Off Cycle
Sign-off requires manual email chains between DVPs, RBMs, and FLMs. A single revision request can stall the cycle by 5–10 business days, delaying rep payments and reducing field-force morale and retention.
📉 No Historical Analytics
Each quarter's data lives in a separate Excel version. Year-over-year performance comparisons, rep attrition analysis, and product-level trend reporting require costly manual consolidation across 8+ files.
📦 Cannot Scale to 70+ Countries
Adding a new quarter regenerates the entire 107KB static data file. Adding a country, product, or promo line requires structural changes to all inter-linked sheets. The current model breaks completely at scale.

## Slide 5
04 | Technical Architecture
End-to-end data flow — from source to delivery
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
5 / 8
DATA SOURCES
DATA PROCESSING
APPLICATION LAYER
OUTPUT
EPD Incentive
File.xlsx
X
CSV Exports
Staff_Input.csv
Promo_Product.csv
Summary_Calc.csv
TCFA.csv
TIC.csv
Manual Uploads
Admin CSV ingestion
⬆
PowerShell
Parser Scripts
CSV → structured data
parse_data.ps1
parse_detailed.ps1
>_
▼
Supabase Migration
Seed Pipeline
seed_supabase.ts
CSV → 13 DB tables
▼
JS Data Files
comprehensive_data.js
data.js
Next.js 14 · App Router · TypeScript
Supabase Auth · Role Guard
DVP | RBM | FLM | Med. Rep.
▼
Filter Engine
Year · Quarter · Rep · Promo Line · Country
▼
Dual-View Renderer
▼
Summary
Dashboard
KPI cards
86 Reps Live
Detailed
View
Rep-level
product breakdown
Product
Promo
Portfolio vs
Plan Achievement
Sign-Off
Workflow
Digital approval
e-signature
Staff
Directory
Roster · Leave
Tracking
▼
Export Engine · Excel (XLSX) · PDF
Web
Dashboard UI
Real-time
incentive portal
🖥️
Incentive
Reports
Per rep / per qtr
breakdown
📄
Export to
Excel
XLSX download
per role scope
📊
Sign-Off
Record
Digital audit
trail PDF
✅
▶
▶
▶

## Slide 6
05 | Risk Register
Identified risks with mitigation strategies
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
6 / 8
#
Risk Description
Likelihood
Impact
Mitigation Strategy
R01
Data quality issues from source CSVs (Cyrillic names, comma-formatted numbers, blank columns)
HIGH
HIGH
Pre-migration data cleanse script; strict TypeScript validators; QA pass comparing DB output vs. source Excel row-by-row.
R02
Supabase service outage or free-tier limitations during critical quarter close
LOW
HIGH
Export read-only Excel fallback at quarter open; Pro-tier upgrade SLA for go-live; nightly pg_dump backups to Supabase Storage.
R03
Scope creep from additional country onboarding (Georgia) or new promo lines mid-quarter
MED
MED
Change-control board approval required; modular schema allows country/region rows without structural changes; phased rollout plan.
R04
User adoption resistance from field force / managers accustomed to Excel workflows
MED
HIGH
Hypercare support during Q1 go-live; in-app contextual tooltips; role-specific training sessions (DVP, RBM, FLM); Excel export always available.
R05
Delay in sign-off chain blocking quarterly payroll processing timelines
LOW
HIGH
Automated email reminders at 48hr & 24hr before deadline; escalation flag in DVP dashboard; offline approval workaround via PDF export.
R06
Security / unauthorized access to sensitive incentive data via misconfigured RLS policies
LOW
HIGH
Supabase Row Level Security enforced at DB layer; penetration test prior to launch; role tokens scoped per user; audit logs enabled.

## Slide 7
06 | Dependency Register
External dependencies required for successful delivery
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
7 / 8
CAT
ID
Dependency Name
Owner
Phase
Status
Description / Notes
T
D01
Supabase Project (Prod)
BSS / IT
Phase 1
PENDING
Production Supabase project with Pro tier subscription. URL & service_role key required for DB schema deployment and seeding.
T
D02
Vercel Deployment Account
BSS / IT
Phase 2
PENDING
Vercel Pro or Abbott-managed hosting for Next.js app. Custom domain (epd-incentive.abbott.com) DNS record required.
T
D03
GitHub Repository & CI/CD
BSS
Phase 1
DONE
GitHub repo (Arslan664/EPD_Incentive_Calculator) is live. GitHub Actions workflow for lint, test, and Vercel deploy to be configured.
D
D04
Complete Q1–Q4 Source CSVs (all quarters)
Abbott KZ Team
Phase 1
PARTIAL
Q1 2017 and Q2 2017 CSVs available. Q3/Q4 and 2018+ data required for full historical load. Georgia (Country 87) records needed.
D
D05
BC_KZ_2017_V10_FINAL.XLSM (External Formulas)
Abbott KZ Team
Phase 1
PENDING
Source Excel file containing linked formula definitions. Required to validate seed script accuracy before DB migration.
P
D06
Abbott DVP Sign-Off on Roles & Access Matrix
Abbott Management
Phase 2
PENDING
Formal approval of RBAC matrix: which role (DVP/RBM/FLM/Rep) sees which data — prerequisite for Supabase Auth configuration.
P
D07
UAT Participants (FLMs & RBMs for pilot quarter)
Abbott KZ HR
Phase 3
NOT STARTED
Minimum 3 FLMs + 1 RBM to conduct structured UAT against Q2 2017 data. Feedback window: 5 business days.
P
D08
Exchange Rate Policy (LC/USD historical locking)
Abbott Finance
Phase 1
PENDING
Decision required: lock historical rates per quarter at ingestion (Q1=314.79, Q2=332.70) or allow finance team override.
STATUS KEY:
DONE
PARTIAL
PENDING
NOT STARTED
CRITICAL

## Slide 8
07 | Current Platform Prototype
Live POC resolving critical pain points
EPD Incentive Platform | Executive Summary | CONFIDENTIAL
8 / 8
POC HIGHLIGHTS
Live Prototype
Configured with Kazakhstan data across 8 quarters. Not just a mockup.
Role-Based Access
Authentication restricts DVP vs RBM vs FLM to their authorized data scope only.
Data Scale
Tracking 86 Medical Representatives, 15 Products, and 6 Promo Lines.
Modern Tech Stack
Built on Next.js 14 (React) with a Supabase (PostgreSQL) backend.
👋 Good Evening, Arslan Sohail (Regional Manager)
Active Reps
86
Total Actual (LC)
78.8M
Total Incentive (LC)
75.0M
Overall Achievement
112.3%
Live Modules Accessible to Role
Performance Dashboard
Detailed summary and breakdowns
Staff Directory
Manage reps, tracking leave, profiles
Product Validation
View portoflio matrices and achievements